## Project Planner
Honors Senior Project Timeline
[7 empty] | Summer |  |  |  |  | Fall Semester | [5 empty] | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Tasks | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Weeks
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Literature review | 1 | 3 |  |  | 0%
Gather users to perform early data gathering | 1 | 4 |  |  | 0%
Prepare documents for early data gathering and low fidelity | 2 | 3 |  |  | 0%
Perform early data gathering | 4 | 2 |  |  | 0%
Neural Network Initial Modelling | 6 | 4 |  |  | 0%
Develop Low fidelity prototype model | 9 | 3 |  |  | 0%
Prepare documents for usablity studies, high fidelity, and future testing | 12 | 4 |  |  | 0%
Testing on Low Fidelity Prototype | 11 | 3 |  |  | 0%
Analytical Evaluation | 14 | 2 |  |  | 0%
Develop High Fidelity Prototype | 15 | 5 |  |  | 0%
Refinement on neural network model | 16 | 2 |  |  | 0%
Usability Testing | 20 | 3 |  |  | 0%
Develop actual web app | 22 | 8 |  |  | 0%
Testing of actual web app | 28 | 3 |  |  | 0%
Deployment of app and model | 32 | 4 |  |  | 0%
Paper and bug fixing | 25 | 13 |  |  | 0%